JISC Project Plan

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Identifier | To be completed by JISC |  |  |
| Project Title | Sustainable Management of Digital Music Research Data |  |  |
| Project Hashtag | SMDMRD |  |  |
| Start Date | 01/10/2011 | End Date | 31/03/2012 |
| Lead Institution | Queen Mary University of London |  |  |
| Project Director | Simon Dixon |  |  |
| Project Manager | Chris Cannam |  |  |
| Contact email | simon.dixon@eecs.qmul.ac.uk | chris.cannam@eecs.qmul.ac.uk |  |
| Partner Institutions | n/a |  |  |
| Project Webpage URL | rdm.c4dm.eecs.qmul.ac.uk |  |  |
| Programme Name | JISC MANAGING RESEARCH DATA PROGRAMME 2011-13 |  |  |
| Programme Manager | Simon Hodson |  |  |

| Document Information |  |  |  |
| --- | --- | --- | --- |
| Author(s) | Simon Dixon | Ivan Damnjanovic |  |
| Project Role(s) | Project Director | Research Assistant |  |
| Date | 07/11/2011 | Filename | SMDMRD-projectplan.doc |
| URL | code.soundsoftware.ac.uk/documents/23 |  |  |
| Access | This report is for general dissemination |  |  |

| Document History |  |  |
| --- | --- | --- |
| Version | Date | Comments |
| 1.0 | 9/11/11 |  |

Table of Contents

NB : This table of contents ‘auto-populates’ - to update the table of contents – place cursor in the table of contents, right-click your mouse, click ’update field’, select appropriate option

TOC \o "1-3" \h \z \u  HYPERLINK \l "_Toc286306590" 1.	Project Overview	 PAGEREF _Toc286306590 \h 3

HYPERLINK \l "_Toc286306591" 1.1	Project Summary	 PAGEREF _Toc286306591 \h 3

HYPERLINK \l "_Toc286306592" 1.2	Objectives	 PAGEREF _Toc286306592 \h 3

HYPERLINK \l "_Toc286306593" 1.3	Anticipated Outputs and Outcomes	 PAGEREF _Toc286306593 \h 3

HYPERLINK \l "_Toc286306594" 1.4	Overall Approach	 PAGEREF _Toc286306594 \h 3

HYPERLINK \l "_Toc286306595" 1.5	Anticipated Impact	 PAGEREF _Toc286306595 \h 3

HYPERLINK \l "_Toc286306596" 1.6	Stakeholder Analysis	 PAGEREF _Toc286306596 \h 4

HYPERLINK \l "_Toc286306597" 1.7	Related Projects	 PAGEREF _Toc286306597 \h 4

HYPERLINK \l "_Toc286306598" 1.8	Constraints	 PAGEREF _Toc286306598 \h 4

HYPERLINK \l "_Toc286306599" 1.9	Assumptions	 PAGEREF _Toc286306599 \h 4

HYPERLINK \l "_Toc286306600" 1.10	Risk Analysis	 PAGEREF _Toc286306600 \h 4

HYPERLINK \l "_Toc286306601" 1.11	Technical Development	 PAGEREF _Toc286306601 \h 5

HYPERLINK \l "_Toc286306602" 1.12	Standards	 PAGEREF _Toc286306602 \h 5

HYPERLINK \l "_Toc286306603" 1.13	Intellectual Property Rights	 PAGEREF _Toc286306603 \h 5

HYPERLINK \l "_Toc286306604" 2	Project Resources	 PAGEREF _Toc286306604 \h 5

HYPERLINK \l "_Toc286306605" 2.1	Project Partners	 PAGEREF _Toc286306605 \h 5

HYPERLINK \l "_Toc286306606" 2.2	Project Management	 PAGEREF _Toc286306606 \h 5

HYPERLINK \l "_Toc286306607" 2.3	Project Roles	 PAGEREF _Toc286306607 \h 6

HYPERLINK \l "_Toc286306608" 2.4	Programme Support	 PAGEREF _Toc286306608 \h 6

HYPERLINK \l "_Toc286306609" 3	Detailed Project Planning	 PAGEREF _Toc286306609 \h 6

HYPERLINK \l "_Toc286306610" 3.1	Evaluation Plan	 PAGEREF _Toc286306610 \h 6

HYPERLINK \l "_Toc286306611" 3.2	Quality Assurance	 PAGEREF _Toc286306611 \h 6

HYPERLINK \l "_Toc286306612" 3.3	Dissemination Plan	 PAGEREF _Toc286306612 \h 7

HYPERLINK \l "_Toc286306613" 3.4	Exit and Embedding Plans	 PAGEREF _Toc286306613 \h 7

HYPERLINK \l "_Toc286306614" 3.5	Sustainability Plans	 PAGEREF _Toc286306614 \h 7

HYPERLINK \l "_Toc286306615" Appendices	 PAGEREF _Toc286306615 \h 7

HYPERLINK \l "_Toc286306616" Appendix A. Project Budget	 PAGEREF _Toc286306616 \h 7

HYPERLINK \l "_Toc286306617" Appendix B. Workpackages	 PAGEREF _Toc286306617 \h 7

Project Overview

1.1	Project Summary

We propose a pilot data-management project for the Centre for Digital Music (C4DM) at Queen Mary University of London. The immediate objectives of this project are: (i) to develop an ongoing management plan for data produced during research at C4DM; (ii) to implement a system for storing and managing such data; (iii) to audit, catalogue, and manage existing data from C4DM using this system. In addition to producing a working data management system and plan, a wider objective is to perform a pilot project toward producing a set of data management methods and recommendations which may be applicable to other research groups within the audio and music research fields in the UK. To this end, any lessons learned and systems developed during this work will be disseminated through the SoundSoftware.ac.uk sustainability project also managed at C4DM.

Objectives

The immediate objectives of this project are:

(i) to develop an ongoing management plan for data produced during research at C4DM;

(ii) to implement a system for storing and managing such data;

(iii) to audit, catalogue, and manage existing data from C4DM using this system.

In addition to producing a working data management system and plan, a wider objective is to perform a pilot project toward producing a set of data management methods and recommendations which may be applicable to other research groups within the audio and music research fields in the UK. To this end, any lessons learned and systems developed during this work will be disseminated through the SoundSoftware.ac.uk sustainability project also managed at C4DM.

Anticipated Outputs and Outcomes

| Output / Outcome Type (e.g. report, publication, software, knowledge built) | Brief Description |
| --- | --- |
| Deliverable D1.1 | Description of data already published by C4DM |
| Deliverable D1.2 | Description of other data produced during recent research but not yet published |
| Deliverable D1.3 | Document specifying C4DM user requirements for research data management |
| Deliverable D2.1 | Summary of current platforms |
| Deliverable D2.2 | Data management system implementation |
| Deliverable D2.3 | User documentation |
| Deliverable D2.4 | Technical report and recommendations for future implementation |
| Deliverable D3.1 | Catalogued data sets available to researchers in C4DM |
| Deliverable D3.2 | Publicly-accessible distributions of catalogued data sets |
| Deliverable D4.1 | Data management plan for C4DM |
| Deliverable D5.1 | Project site and feed |
| Deliverable D5.2 | Blog posts, reports, budgets, plans, etc., as required by JISC |

Overall Approach

Data at the Centre for Digital Music

The Centre for Digital Music (C4DM) at Queen Mary University of London is one of the leading research centres in the field of audio and music technology and signal processing. C4DM makes use of a variety of data as research inputs—most obviously audio datasets—and produces a variety of types of data as research outputs. These outputs include: (i) manually annotated feature data (“reference annotations”) such as expert chord and key transcriptions of existing music recordings which are used as comparative data for evaluating research work, and (ii) automatically produced annotations such as those accompanying the publication of methods for audio feature analysis. C4DM also publishes some “data sets” which are actually software services calculating data dynamically or on demand, such as those provided by the SAWA (Sonic Annotator Web Application, www.isophonics.net/sawa/) feature extractor and the JISC-funded LinkedBrainz project (linkedbrainz.c4dmpresents.org).

With this project, we aim to improve the efficiency and sustainability of storage and publication efforts for those data sets produced as research outputs. We will not be handling audio data (which generally can not be published, due to copyright restrictions) or data that is generated dynamically, e.g. by web services, in this project. We believe this restriction is appropriate given the short timescale of the present project and its interaction with ongoing work funded by other grants (namely the Sound Software project described below). We anticipate that outcomes from this work will prove relevant for other types of research data. In subsequent work in the Sound Software project, we intend to build on this project to cover further data types.

The two classes of research data to be considered here are therefore: (i) reference annotations produced within C4DM as discrete pieces of work; (ii) data accompanying research publications, such as the results of experiments, evaluation data, or representative outputs of an algorithm. The common theme is that these data originate in C4DM and are to be published externally.

Reference Annotations

C4DM publishes a number of reference annotations, listed at http://isophonics.net/datasets/, and plans to produce more in general ongoing work. Examples to date include annotations of harmony (chords and keys), rhythm (beats and bars), and structural boundaries (e.g. verse and chorus), covering the Beatles catalogue, and a number of songs from Queen, Carole King, and Michael Jackson. These annotations are used widely in the research community for evaluating algorithms for automatic analysis of audio, including in the international MIREX evaluations (Music Information Retrieval Evaluation eXchange, www.music-ir.org/mirex).

The annotations are transcribed by expert listeners attending closely to musical recordings using interactive software such as Sonic Visualiser (www.sonicvisualiser.org), a process that takes a significant amount of time and care. Such data typically have an associated level of confidence, based on how thoroughly the results have been checked, but depending also on the intrinsic ambiguity of the musical information being described. The data are associated with specific releases of musical recordings, although these often cannot be shared for legal reasons. (To use the data, researchers must purchase the matching recordings using the release information supplied, such as CD and track numbers, titles and artists.)

Annotation data may be updated and should be versioned; the existing published data have in some cases been updated multiple times as corrections and additions are made. This is a normal situation which must be allowed for, as human annotators can not be expected to produce perfect work.

Currently C4DM has only informal methods for describing and distributing reference annotations through its Isophonics web site. Files are simply copied to the web server with the descriptive information entered in the Drupal-based website. There is no policy for managing descriptive metadata, no properly maintained storage facility for such data, and no effective policy in place for backup or versioning.

Research Data

C4DM has produced several hundred refereed research publications in the last decade, but only a small number of associated data sets have been published. A combination of reasons could be cited for this, including failure to understand the benefits of data publishing, the lack of suitable infrastructure for managing and preserving research data, and the lack of impetus from main funding bodies (EPSRC and EU) and journals, who do not require data publication. Growing awareness of the principles of Reproducible Research applied to digital music research have led to isolated examples of publishing research data, such as the automatic chord transcriptions at www.isophonics.net/content/automatic-annotations, however this is the exception rather than the rule.

Output from automatic feature extraction algorithms is usually summarised for paper publications as a set of statistics describing the extent to which the output concurs with a set of manual annotations. This is a useful measure of progress in algorithm development, and is used for example in the MIREX series of international evaluations of music information retrieval algorithms (www.music-ir.org/mirex). Such statistics do not, however, tell the whole story: they fail to inform readers about which musical examples were analysed successfully, and which examples the algorithm failed on. Characterisation of successes and failures is necessary in order to gain insight about how systems can be improved. Further, a difference in mean performance of two different algorithms is less revealing than a piecewise comparison of algorithm performance, from the viewpoint of both informal and formal statistical analysis. Other reasons for data publication are to allow verification of published results and testing of reimplementations of published algorithms. Finally, algorithm outputs are needed by researchers who wish to assess others’ work using different criteria or metrics than those appearing in their publications.

Anticipated Impact

| Impact Area | Anticipated Impact Description |
| --- | --- |
| Maintain research excellence | The success of the project will be recognised through the increased publication and dissemination of research data in C4DM, and the concrete recommendations for improving best practice which are fed into the Sound Software project and JISC community. |
| Be more effective / save money | The efficient management of research data will save researchers' time (and thus money) when e.g. attempting to repeat their own or others' experimental results. |
| Have a positive impact on wider society | The best practice developed in the data management plan will lead to more efficient and effective publicly funded research; i.e. it will have a magnifying effect on many research efforts. Also the dissemination of data management principles to the research community will enable the benefits of the project to be multiplied at other sites. |

Impact Areas : maintain research excellence; maintain teaching & learning excellence; be more effective/save money; have a positive impact on wider society; be ready for technology needs in the future.

Stakeholder Analysis

| Stakeholder | Interest / stake | Importance (H/M/L) |
| --- | --- | --- |
| Researchers (academics, post-doctoral research assistants, PhD students and MSc students) in the Centre for Digital Music (C4DM) | Currently, minimal support is provided for these tasks: C4DM has no data management plan, no versioning of reference annotations, no structure for organising storage, no automatic backup facilities for research data, and only a simple web-server for making data available to other researchers. As a result, much research data is never published, and is often not even available internally, as it resides in the personal file space of researchers, and can be lost when people change institutions. | H |
| Other research groups within the audio and music research fields and also the wider JISC and HE communities | We expect the data management methods and recommendations produced by the current pilot project to be applicable to other research groups within the audio and music research fields, and also to the wider JISC and HE communities. In order to facilitate transfer of any lessons learned and systems developed during this work, we will make use of dissemination channels provided by the SoundSoftware.ac.uk sustainability project managed at C4DM and the Digital Music Research Network (www.elec.qmul.ac.uk/dmrn/), as well as through regular JISC channels . | H-M |

Related Projects

The Sound Software Project

C4DM is currently managing an EPSRC-funded Software Sustainability project, “Sustainable Software for Digital Music and Audio Research” (EPSRC grant EP/H043101/1), known as the Sound Software project, with a public site at http://soundsoftware.ac.uk/. This project, funded until 2014, aims to provide resources, advice, and training to facilitate the development and use of software, data, and metadata in the UK audio and music research community. The focus of the Sound Software project is primarily on software resources, building the code.soundsoftware.ac.uk repository and facilities amongst other work, but managing research data is a complementary task which fits with the overall aims of the project.

The results from the current project shall be disseminated via the Sound Software project and used as a basis for resources to be made available to other research groups in this field. We also plan to build on this work to cover a wider range of data types, including audio.

We believe that we can take advantage of the obvious affinity between the present project and the Sound Software project in order to enhance the sustainability of this work and of the research output from C4DM. Effectively, this is a pilot project carried out within the Centre for Digital Music on its own research data sets with its own concrete research requirements, aimed at providing lessons in good practice and a viable data management plan and system implementation which can be drawn upon by Sound Software in providing recommendations and facilities for other groups.

The existence of the Sound Software project also informs our selection of the types of data to focus on for this project. By focusing on research outputs of C4DM, we can pilot some generally applicable data management techniques in a context (data specific to this group’s work) that the Sound Software project would not otherwise be directly involved in.

Constraints

With this project, we aim to improve the efficiency and sustainability of storage and publication efforts for those data sets produced as research outputs. We will not be handling audio data (which generally can not be published, due to copyright restrictions) or data that is generated dynamically, e.g. by web services, in this project. We believe this restriction is appropriate given the short timescale of the present project and its interaction with ongoing work funded by other grants (namely the Sound Software project described below). We anticipate that outcomes from this work will prove relevant for other types of research data. In subsequent work in the Sound Software project, we intend to build on this project to cover further data types.

Assumptions

The project is limited to 6 months duration, so it cannot be more than a pilot project. It is hoped that a suitable software platform will be found that can be adapted for use at C4DM. In this case, it will be possible to implement a usable data management system within the duration of the project. Otherwise, it will be only possible to produce a prototype solution.

Also, we plan to deal only with research data produced as outputs at C4DM. In particular, we will not be handling audio data (which generally can not be published, due to copyright restrictions) or data that is generated dynamically, e.g. by web services.

Risk Analysis

| Risk Description | Probability (P) 1 – 5 (1 = low 5 = high) | Severity (S) 1 – 5 (1 = low 5 = high) | Risk Score (PxS) | Detail of action to be taken (mitigation / reduction / transfer / acceptance) |
| --- | --- | --- | --- | --- |
| Unable to recruit staff | 3 | 5 | 15 | As expected, we have been able to recruit staff from the beginning of the project, despite the tight deadlines involved. In the event of one of the researchers leaving the project, we have a number of unsuccessful applicants who were deemed employable as well as a number of recent PhD graduates and postdocs within the group who might be available if needed. In case of recruitment delays, we might be able to reallocate staff from other projects. |
| Software development deadlines not met | 2 | 3 | 6 | The project will have access to software development support from the Sound Software project through the CI (Cannam) and another experienced developer in the Sound Software group. This group will be available to carry out any further development required after the end of this project. If the data management system (WP2) is not working in time to carry out WP3, a simpler database solution will be employed. |
| Software system rejected by users | 3 | 3 | 9 | Mitigated by working with users to establish requirements (WP1.2, WP1.3) and to test the prototype (WP2.4) during development iterations. |
| Management difficulties encountered | 1 | 5 | 5 | The PI has experience of managing the JISC-funded Linked Music Metadata project (2010-11) and RCUK- funded Musicology for the Masses (2010-12), and as CI of several national and international projects. CI (Plumbley) is director of C4DM and has extensive project management experience. |

Technical Development

The level of technical development required for the project has yet to be ascertained, as it will depend on the requirements analysis currently being undertaken, and the survey of existing research data management systems. Through close cooperation with the soundsoftware.ac.uk project, we will ensure that appropriate software development processes and standards are followed.

Standards

The project is committed to the use of open standards and open source software. We have not yet identified any relevant standards, but will review these as the candidate software platforms for research data management are assessed.

| Name of standard or specification | Version | Notes |
| --- | --- | --- |

Intellectual Property Rights

It is planned to use open source software in this project, so it is not anticipated that any third party rights will need to be negotiated. Similarly, any software or other IP generated in the project is planned to be released under an open source license.

Project Resources

2.1	Project Partners

None

Project Management

The project will be managed on a day-to-day basis by the PI (Dixon) and CI (Cannam), with project meetings held weekly to assess progress and problems. This has been our practice throughout the Sound Software project and previous JISC-funded projects. The CIs (Plumbley and Cannam) will participate in the management process to ensure compatibility and continuity with the requirements of the Sound Software project from a management and technical perspective respectively.

Project Roles

| Team Member Name | Role | Contact Details | Days per week to be spent on the project |
| --- | --- | --- | --- |
| Dr Simon Dixon | Principal Investigator, Project Director | Tel: +44 (0) 20 7882 7681 Email: simon.dixon@eecs.qmul.ac.uk | 0.5 |
| Prof Mark D Plumbley | Co-Investigator | Tel: +44 (0) 20 7882 7518 Email: mark.plumbley@eecs.qmul.ac.uk | 0.25 |
| Chris Cannam | Co-Investigator, Project Manager | Email: chris.cannam@eecs.qmul.ac.uk | 0.5 |
| Dr Marco Fabiani | Researcher | Email: marco.fabiani@eecs.qmul.ac.uk | 5 |
| Dr Ivan Damnjanovic | Researcher | Email: ivan.damnjanovic@eecs.qmul.ac.uk | 5 |

Programme Support

None

Detailed Project Planning

3.1	Evaluation Plan

As this is a short (6 month) pilot project, evaluation will be summative, towards the end of the project. Further, the impact of the project is not likely to be felt until after the project has finished, involving the uptake of the data management plan and use of the pilot management system.

| Timing | Factor to Evaluate | Questions to Address | Method(s) | Measure of Success |
| --- | --- | --- | --- | --- |
| Month 5 | Successful implementation of data management system | Does it satisfy user requirements gathered in WP1.3 and specified in WP2.2? | Successive prototypes will be given to small numbers of users for testing and evaluation (see WP2.4) | User acceptance |
| Month 6 | Publication of research data | Has new or existing research data been published using the system? | As part of the cataloguing in WP3, suitable data sets entered into the data management system will be released publicly (see WP3.2) | Public release of C4DM research data sets |
| After project end | Adoption of data management plan | Is the ongoing management of research data in accordance with the plan? Has it been adopted as policy in C4DM? Are other groups able to use the plan or its principles? | Observation; discussion will colleagues in Digital Music Research Network. | Success if plan is adopted or the best practice informs future policy of research groups. |

3.2	Quality Assurance

| Output / Outcome Name | When will QA be carried out? | Who will carry out the QA work? | What QA methods / measures will be used? |
| --- | --- | --- | --- |
| Data management system | End of month 5 | Project manager (Chris Cannam) | Test compliance with user requirements and specifications, including interoperability with the SoundSoftware.ac.uk project, open source principles, best software engineering practice, as appropriate to a pilot project |
| Research data catalogue | End month 6 | CI Plumbley (Director of C4DM) | Check fitness for ongoing use by C4DM |
| Data management plan | End month 6 | CI Plumbley (Director of C4DM) | Check fitness for ongoing use by C4DM |

3.3	Dissemination Plan

General external communications will be through regular posts on a dedicated blog for the project, linked to the C4DM and Sound Software sites and Twitter/RSS feeds. Project deliverables will be published on the project site, archived by Sound Software, and shared with the DCC and with other interested parties via JISC channels (e.g. Strand and Programme Meetings, Research Data Management Forum events, direct engagement with other funded projects). Outputs from the project will also be disseminated at conferences and workshops such as the annual Digital Music Research Network meeting, hosted at Queen Mary University of London in December, and the International Digital Curation Conference.

| Timing | Dissemination Activity | Audience | Purpose | Key Message |
| --- | --- | --- | --- | --- |
| 20 Dec | Poster presentation at Digital Music Research Network meeting | UK Digital Music research community | Raise awareness of project; disseminate any early outcomes | "Watch this space" (i.e. we expect final outcomes of project to be useful for the community) |

3.4	Exit and Embedding Plans

| Project Outputs/Outcomes | Action for Take-up & Embedding | Action for Exit |
| --- | --- | --- |
| Data management system | Investigation of possible integration with SoundSoftware.ac.uk project | Hand over system to SoundSoftware project |
| C4DM research data catalogue | Release to C4DM and/or wider research community as appropriate | Assign responsibility for maintenance; or if possible, integrate into automatic management system |
| C4DM data management plan | Discussion with C4DM Director and academics | Establishment of data management policy for the C4DM, to be ratified by head of group. |

3.5	Sustainability Plans

| Project Outputs | Why Sustainable | Scenarios for Taking Forward | Issues to Address |
| --- | --- | --- | --- |
| Data management system | Integrated into SoundSoftware.ac.uk project | Work closely with SoundSoftware project throughout the project | Technical issues with integration, as they arise |
| C4DM research data catalogue | Ongoing useful resource for researchers; can be maintained simply e.g. by wiki or automatically by data management system | Investigate possibility of automation of catalogue via data management system | Responsibility for maintainence; minimisation of effort required |
| C4DM data management plan | To be used on an ongoing basis at C4DM and updated as part of strategic management of research group | Discussion with C4DM Director and academic staff | Dissemination to wider audience |

Appendices

Appendix A. Project Budget

One full-time postdoctoral research assistant (RA) with experience of the working practices of the Centre for Digital Music or another research group in the same field is required for the 6-month duration of the project. This RA will carry out work packages 1, 3, and 4, and will participate in work package 5.

One full-time software developer (SD) is required for the 6-month duration of the project. This developer will carry out work package 2 and will participate in work package 5.

The time allocation for the PI (Dixon) is factored at 10% which will be used for project management, staff management, reporting and research, as well as attendance at the launch meeting, JISC Programme/Strand meetings, meetings with the Programme Manager and dissemination and evaluation events.

The CIs (Plumbley and Cannam) will be involved in the liaison with the Sound Software project, in particular Plumbley (PI of Sound Software) will deal with the management and planning aspects (5%), while Cannam’s role will be to guide and advise the software development process and to manage handover of any outcomes to Sound Software for further work and subsequent dissemination (10%).

The directly allocated costs include technical support at 5% for software installation, account management, networking and other computing infrastructure, and administrative support at 5% for assisting with recruiting, organisation of travel and financial reporting.

Under hardware/software we request two laptop computers for the RA and SD to be used for development work, document preparation, presentations, and demonstrations. We request Lenovo ThinkPad T420i HD+ (£814) for this purpose, and allow £500 for any necessary software licences or other consumables.

| Directly Incurred Staff | TOTAL £ |
| --- | --- |
| Postdoc RA, Grade 5, 825 hours, 100% FTE Software Developer, Grade 3, 825 hours, 100% FTE Researcher, Grade 6, 83 hours, 10% FTE | 21571 18816 2696 |
| Total Directly Incurred Staff (A) | 43082 |
| Non-staff | TOTAL £ |
| Travel and expenses Hardware/software Dissemination Evaluation Other | 1000 2128 0 0 1500 |
| Total Directly Incurred Non-staff (B) | 4628 |
| Directly Incurred Total (C=A+B) | 47710 |
| Directly Allocated | TOTAL £ |
| Staff Estates Other | 8220 6937 477 |
| Total Directly Allocated (D) | 15634 |
| Indirect Costs (E) | 25308 |
| Total Project Cost (C+D+E) Amount Requested from JISC Institutional Contributions | 88652 79429 9223 |
| No. FTEs used to calculate indirect and estates charges, and staff included | 1.05 (annualised) RA (0.5) SD (0.5) PI (0.05) |

For travel, we request the cost of the project team attending JISC events (Programme meetings, dissemination events, evaluation activities) and local conferences and meetings, which we estimate will amount to £1000. Thus the costs of dissemination and evaluation are included under “Travel and expenses”. The £1500 under the heading “Other” is requested to cover advertising and recruitment expenses.

The project will benefit the institution in several ways: first, the implementation of a data management strategy will increase the effectiveness of researchers, saving them time when reusing research data and protecting against data loss. It will also increase the prestige and number of citations of C4DM research by making research data available to the research community. The complementary Sound Software project will be benefitted by the wider scope of producing a data management plan, which was not envisaged in the original scope of the project.

The time of the CIs (Plumbley and Cannam) is covered by Queen Mary as an institutional contribution to the project. Cannam is counted at 10% and Plumbley 5% for the 6-month duration of the project. Including indirect costs, estates and other charges, this amounts to an institutional contribution of £9223. In addition, C4DM will provide access to large-scale storage and network facilities as an in-kind contribution.

Appendix B. Workpackages

WP1: Requirements analysis (Months 1–2; RA)

WP1.1 Audit of data already published by C4DM: The data published and disseminated by C4DM through existing outlets will be listed and described informally, with common qualities as well as potentially troublesome qualities for metadata description highlighted in the description.

WP1.2 Audit of unpublished data: Authors of papers published during the previous 12 months will be interviewed and an audit made of data referred to in their papers or produced during research which has not yet been made available to the public, or of data published but not yet aggregated in the usual location for C4DM datasets (at isophonics.net).

WP1.3 Requirements analysis for access, re-use and publication of research data: We will analyse the requirements of the authors interviewed in WP1.2, based on their use of existing research data, their knowledge of existing best practice, and any problems they have experienced in obtaining or using data from other researchers, or in making their own data available and visible to the research community. Based on WP1.2, we will determine requirements for data (types, quantity) in order to maximise the likelihood of acceptance of the proposed system by the user community.

WP2: System design and implementation (Months 1–6; SD)

WP2.1Reviewofcurrentplatforms:Arapidinformalsurveyofexistingdata-managementplatformsand current practices, whether arising from prior JISC project outputs (e.g. MaDAM, ADMIRAL, DryadUK) or from the community at large, will be carried out and the appropriateness of each platform to the types of data being managed at C4DM will be evaluated. The Digital Curation Centre will also be consulted for advice about suitable platforms. Three possible outcomes are foreseen: (i) a suitable platform is found and chosen for the project; (ii) a platform is found that requires modification in order to make it suitable for the project; and (iii) no suitable platform is found, and the system has to be built using generic tools.

WP2.2 Technical requirements gathering and system design: The requirements process will consider the qualities of data identified during WP1, the needs of users within C4DM (WP1.3), the ability to manage backups and to publish data externally, and the hardware infrastructure available. These will be used to propose a candidate implementation. The technical requirements process will be carried out in consultation with early data management plan (DMP) development (see WP4 below) in order to promote reusability of the technical work and test the practicality of recommendations for the DMP. Given the short timescale, systems building upon existing software and deployment practices identified during WP2.1 will be preferred. Preference will also be given to open standards for storage and description, to open source software, and to software that interoperates with other systems within C4DM and with platforms being developed and deployed by the Sound Software project. It is understood that the system developed will be a pilot implementation with a goal of learning lessons for future work as much as of satisfying current requirements.

WP2.3 Implementation and integration: Development and deployment of the system to satisfy the requirements established in WP1.3 and WP2.2, using a rapid prototyping methodology. Any bespoke software developed will be published under an open source licence.

WP2.4 User acceptance testing: The system will be opened to the project RA, and handed to a pool of approximately 4 active researchers within C4DM for evaluation and to obtain feedback. This process will overlap with WP2.3 and will inform successive iterations of the software.

WP2.5 Documentation and Recommendations: The system will be documented for end users, its technical design will be described in a short report, and a set of recommendations for future implementations (including details from user feedback and experiences with WP3, below) will be compiled. Feedback from WP2.4 will be incorporated into this documentation. The recommendations will also be disseminated to stakeholders via the Sound Software project, the Digital Music Research Network and JISC Programme meetings.

WP3: Data cataloguing (Months 4–6; RA)

The data listed during the audit of WP1 will be entered into the system developed in WP2, with metadata following existing schema standards where possible and in line with the recommendations being developed for the DMP in WP4. Data that are to be made publicly available will be linked through to an externally visible web resource.

WP4: Development of data management plan (Months 2–6; RA)

A data management plan for C4DM will be developed, detailing issues such as the responsibilities of researchers and managers, conventions for specifying ownership and access rights, means of protection of personal data, version control and quality control.

WP5: Communication and Management (Months 1–6; PI, CI, RA, SD)

WP5.1 Project management: The project will be managed on a day-to-day basis by the PI (Dixon), with project meetings held weekly to assess progress and problems. This has been our practice throughout the Sound Software project and previous JISC-funded projects. The CIs (Plumbley and Cannam) will participate in the management process to ensure compatibility and continuity with the requirements of the Sound Software project from a management and technical perspective respectively.

WP5.2 Dissemination: General external communications will be through regular posts on a dedicated blog for the project, linked to the C4DM and Sound Software sites and Twitter/RSS feeds. Project deliverables will be published on the project site, archived by Sound Software, and shared with the DCC and with other interested parties via JISC channels (e.g. Strand and Programme Meetings, Research Data Management Forum events, direct engagement with other funded projects). Outputs from the project will also be disseminated at conferences and workshops such as the annual Digital Music Research Network meeting, hosted at Queen Mary University of London in December, and the International Digital Curation Conference.

Project Identifier: SMDMRD

Version: 1.0

Contact: Simon Dixon

Date: 2/11/2011